## Schedule of Values
Schedule of Values
| Project Name: |  |  |  | Application #:
| Project #: |  |  |  | Application Date:
| Contractor: |  |  |  | Period to:
Item # | Description of Work | Scheduled Value | WORK COMPLETED |  | Stored Materials (not in D or E) | Total Completed & Stored to Date | % Complete | Balance to Finish | Retainage
|  |  | Previous Application | This Period |  |  |  |  | 10%
9970 | Demolition | 3000 | 2000 | 0 | 0 | 2000 | 66.67% | 1000 | 200
9955 | Drywall & Carpentry | 36000 | 11000 | 4200 | 1800 | 17000 | 47.22% | 19000 | 1700
9940 | Doors & Hardware | 1000 | 0 | 500 | 0 | 500 | 50% | 500 | 50
9943 | Electrical | 7000 | 1000 | 3000 | 850 | 4850 | 69.29% | 2150 | 485
Totals |  | 47000 | 14000 | 7700 | 2650 | 24350 | 51.81% | 22650 | 2435
Guide to using Schedule of Values Template:
Columns A, B, C: In these columns, enter the item number, description, and estimated cost for each line item. Each line can represent items of work or subcontractors.
Column D: In this column, enter the amount of work that was listed as completed in previous pay applications. If there were no previous applications, you can leave this column blank.
Column E: In this column, enter the amount of work completed in the current period. This should include all work completed by the application date that was not included in any previous pay applications.
Column F: In this column, enter the value of stored materials for which you are seeking payment. Do not include the value of materials that are accounted for in columns D or E.
Column G: This column calculates the total amount of the completed work and stored materials. (D + E + F)
Column H: This column calculates the percent of work completed. (G ⁒ C)
Column I: This column calculates the value of work still remaining until completion. (C - G)
*Column J: When the project contract allows retainage to be calculated on a line-item basis, enter the retainage percent into cell J10 to calculate retainage for each line item. If instead retainage is withheld from the overall contract amount, change cell J11 to 0.